## Team agreement
Team Norms |  | Notes
Project Name: |  | 50 - Non-intrusive Residential Power Disaggregation
Team project google folder link |  | Link
Mode of regular team meetings |  | Google Meets (Recurring Meeting to be set after 1st meeting)
Mode for urgent communications |  | Discord, Text
Project management rules
Meeting scheduling- How to resolve everybodies schedule conflicts |  | Share schedules in drive, decide on a time that works for everyone
How much notice should be given if a team member cannot attend a team meeting? |  | As soon as possible, but not less than 24 hours
When is a team member late to a team meeting and what are the consequences? |  | 10 minutes is considered late, team member will be recorded as absent
What to do when action items are not complete when agreed? |  | Item will be recorded as incomplete by the original assignee. Item will be reassigned
How long before assignments are due will the work be divided among team members? |  | Minimum of 7 days, ideally when assignment is created
How long before the assignment is due will the draft be ready for team review? |  | Minimum of 3 days
Project Management Roles |  |  | Technical roles - To be determined
| Team Leader | Andrew Bailey
| 1. Meeting minutes taker and Agenda manager | Andrew Bailey | ML - Model and Training
| 2. Sponsor Contact and Meeting Scheduler | Ralph Cullom | Website/UI
| 3. Purchasing contact | Manny Harris | Data Communication/Storage
| 4. Website and Google folder Manager | Labib Kasim | ML- Data handling and preprocessing
Ideas and activities for getting to know each other
1. Class
2. Dinner
3. Bar

## Project Timeline_F23
PROJECT STATUS
PROJECT TITLE: |  | Non-intrusive Residential Power Disaggregation | [5 empty] | Project Number: |  |  |  | 50 | [7 empty] | * Estimated dates | [7 empty] | Legend |  |  |  | Solid dark red fill = behind
Team Members: |  | Andrew Bailey, Ralph Cullom, Manny Harris, Labib Kasim | [5 empty] | Revision Date: |  |  |  | 2024-02-26
Team leader: |  | Andrew Bailey
| Subsystem Name |  |  | Task ID | Task detail | Owner | Task Dependency | [11 empty] | Q2 | [12 empty] | Q3 | [11 empty] | Q4
[8 empty] | AUG |  | SEPT |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN |  |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  |  | JUN |  |  |  | JUL
[5 empty] | PROJECT WEEK --> |  |  | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31
[5 empty] | ECE Semester |  |  | AUG 22: FALL 2023; DEC 19: WINTER Break; JAN 9: SPRING 2023; MAY 8: SUMMER Break
1 | Class Milestones |  |  |  | Project agreement |  |  | SEPT 5: TRUE
[5 empty] | Project Requirements Document & Market Slides |  |  | SEPT 26: TRUE
[5 empty] | System Architecture Diagrams |  |  | OCT 3: TRUE
[5 empty] | Preliminary Design Review |  |  | OCT 10: TRUE
[5 empty] | Status review |  |  | OCT 24: TRUE
[5 empty] | Critical Review |  |  | NOV 28: TRUE
[5 empty] | CDR |  |  | JAN 30: TRUE
[5 empty] | Program Review 1 |  |  | FEB 6: TRUE
[5 empty] | Program Review 2 |  |  | FEB 20: TRUE
[5 empty] | Alpha Demo |  |  | MAR 6: TRUE
[5 empty] | Program Review 3 |  |  | MAR 27: TRUE
[5 empty] | Beta Demo |  |  | APR 3: TRUE
[5 empty] | Design Day |  |  | APR 10: FALSE
[5 empty] | Final Docs and Return of Items |  |  | APR 17: FALSE
2 | Machine learning A:Model & Data Handling (Andrew) B:Weather API and Preprocessing (Labib) Backups: Ralph & Manny |  | A | MA1 | Create an inital model using customer 1 data | Andrew |  | OCT 31: 100%
|  |  |  | MA2 | Create validation method for actual vs. predicted | Andrew |  | OCT 31: 100%
|  |  |  | MA3 | Explore other model types | Andrew | MA1,MA2 | DEC 5: 100%
|  |  |  | MA4 | Choose best or combination of models | Andrew | MA3 | JAN 16: 100%
|  |  |  | MA5 | Read/write data from InfluxDB cloud | Andrew |  | JAN 16: 100%
|  |  |  | MA6 | Consolidate all training data | Andrew |  | JAN 23: 100%
|  |  |  | MA7 | Train final model with consolidated data | Andrew |  | FEB 6: 100%
|  |  |  | MA8 | Train model with weather history as a feature | Andrew, Labib | MA4,MD5 | FEB 13: 100%
|  |  |  | MA9 | Read measurement data from influxDB local | Andrew, Manny | DC4 | FEB 27: 100%
|  |  |  | MA10 | Write prediction data back to influxDB local | Andrew, Manny | MA9, DC4 | MAR 6: 100%
|  |  |  | MA11 | Export final trained model | Andrew | MA6,7,8 | MAR 6: 100%
|  |  |  | MA12 | Run machine learning model real time | Andrew, Labib | MA9,10,11 | MAR 20: 100%
|  |  |  | MA14 | Run python scipt (ML and Data Handling) as windows application | Andrew, Manny, Labib | MA12, DC6 | APR 3: 100%
|  |  | B | MD1 | Research trade-offs between different data source and finalize on one for pre-processing before it goes into ML model | Labib |  | NOV 7: 100%
|  |  |  | MD2 | test out code for a test file and make sure its meeting all the requirements | Labib | MD1 | DEC 5: 100%
|  |  |  | MD3 | figure out how to integrate my task with the other subtasks, and other constraints | Labib | MD1 | JAN 9: 100%
|  |  |  | MD4 | Add temperature history column to training data based off timestamp | Labib |  | JAN 30: 100%
|  |  |  | MD5 | Use weather API to get real time temperature data and future temperature predictions | Labib |  | FEB 20: 100%
|  |  |  | MD6 | add columns predicting costs and another set of columns for individual energy based on the measurements given for each individual appliances using Python | Labib | MA5, MA6 | FEB 20: 100%
|  |  |  | MD7 | Run python scipt (ML and Weather API) on external hardware (RPi) | Labib | MD5, MA9 | bar: MAR 13 to APR 3
3 | Data Communication Lead:Manny Backup:Andrew |  |  | DC1 | Configure InfluxDB database | Manny |  | OCT 17: 100%
|  |  |  | DC2 | Get ESPHome running on ESP32 | Manny |  | NOV 7: 100%
|  |  |  | DC3 | Add MQTT input plugin | Manny |  | DEC 19: 100%
|  |  |  | DC4 | Write Homeassist OS to SD Card using RPI imager | Manny |  | JAN 30: 100%
|  |  |  | DC5 | Use SD card to install Home Assistant OS on RPi | Manny | DC4 | FEB 13: 100%
|  |  |  | DC6 | Create Home Assistant account and learn the basics of the software | Manny | DC5 | FEB 13: 100%
|  |  |  | DC7 | Install Grafana, InfluxDB, and ESPHome add ons to Home assistant | Manny | DC6 | FEB 27: 100%
|  |  |  | DC8 | Connect ESP32 to Home Assistant | Mann7 | DC6 | MAR 6: 100%
|  |  |  | DC9 | Send measurements from CT board to Home Assistant using ESPHome that is installed on ESP32 | Manny | DC7 | MAR 6: 70%
|  |  |  | DC10 | Show data being recorded and uploaded to influxDB as it is being measured | Manny | DC8 | MAR 20: 10%
4 | Website/UI Lead:Ralph Backup:Labib |  |  | WU1 | Create communication between InfluxDB and Grafana | Ralph | W1 | NOV 14: 100%
|  |  |  | WU2 | Create graph presets | Ralph | W2 | DEC 12: 100%
|  |  |  | WU3 | Display Influx cloud data | Ralph | W3 | JAN 30: 100%
|  |  |  | WU4 | Display data on grafana local from influxdb local | Ralph | DC4 | FEB 13: 100%
|  |  |  | WU5 | Update Grafana dashboard to suit device requirements | Ralph | WU5 | MAR 6: 100%
|  |  |  | WU6 | Display costs info | Ralph |  | MAR 20: 100%
|  |  |  | WU7 | Stress test Grafana Demo for Design Day | Ralph |  | MAR 27: 75%

## Task List
Project Name: | 50 - Residential Power Disaggregation
Team Members: Andrew, Ralph, Manny, Labib
Subsystem | Task # | Task | Owner(s) | Date Due | Dependencies | Done?
Machine Learning - Model (lead - Andrew, Support - Ralph)
| MA1 | Create an inital model using customer 1 data | Andrew | 2023-11-28 |  | TRUE
| MA2 | Create validation method for actual vs. predicted | Andrew | 2023-11-07 |  | TRUE
| MA3 | Explore other model types | Andrew | 2023-12-12 | MA1,MA2 | TRUE
| MA4 | Choose best or combination of models | Andrew | 2024-01-09 | MA3 | TRUE
| MA5 | Read/write data from InfluxDB cloud | Andrew | 2024-02-03 |  | TRUE
| MA6 | Consolidate all training data | Andrew | 2024-02-20 |  | TRUE
| MA7 | Train final model with consolidated data | Andrew | 2024-03-01 |  | TRUE
| MA8 | Train model with weather history as a feature | Andrew | 2024-03-12 | MA4,MD5 | TRUE
| MA9 | Read measurement data from influxDB local | Andrew, Manny | 2024-03-21 | DC4 | TRUE
| MA10 | Write prediction data back to influxDB local | Andrew, Manny |  | MA9, DC4 | TRUE
| MA11 | Export final trained model | Andrew |  | MA6,7,8 | TRUE
| MA12 | Run machine learning model real time | Andrew |  | MA9,10,11 | TRUE
| MA14 | Run python scipt (ML and Data Handling) as windows application | Andrew, Labib, Manny | 2024-03-25 | MA12, DC6 | TRUE
Machine Learning - Preproccessing & pipelining (lead - Labib, Support - Manny)
| MD1 | Research trade-offs between different data source and finalize on one for pre-processing before it goes into ML model | Labib | 2023-11-14 |  | TRUE
| MD2 | test out code for a test file and make sure its meeting all the requirements | Labib | 2024-01-02 | MD1 | TRUE
| MD3 | figure out how to integrate my task with the other subtasks, and other constraints | Labib | 2024-01-30 | MD1 | FALSE
| MD4 | Add temperature history column to training data based off timestamp | Labib, Ralph | 2024-02-14 | MD5 | FALSE
| MD5 | Use weather API to get real time temperature data and future temperature predictions | Labib | 2024-03-05 |  | TRUE
| MD6 | add power cost analyses column for each individual appliances | Labib | 2024-03-05 | MA5, MA6 | FALSE
| MD7 | Run python scipt (ML and Weather API) on external hardware (RPi) | Labib, Andrew, Manny | 2024-03-25 | MD5, MA9 | FALSE
Data Communication (lead - Manny, Support - Andrew)
| DC1 | Configure InfluxDB database | Manny | 2023-11-14 |  | TRUE
| DC2 | Get ESPHome running on ESP32 | Manny | 2023-11-22 |  | TRUE
| DC3 | Add MQTT input plugin | Manny | 2024-01-10 |  | TRUE
| DC5 | Use SD card to install Home Assistant OS on RPi | Manny, Andrew | 2024-02-14 | DC4 | TRUE
| DC7 | Install Grafana, InfluxDB, and ESPHome add ons to Home assistant | Manny, Andrew | 2024-02-20 | DC6 | TRUE
| DC9 | Send measurements from CT board to Home Assistant using ESPHome that is installed on ESP32 | Manny | 2024-03-05 | DC7 | FALSE
| DC10 | Show data being recorded and uploaded to influxDB as it is being measured | Manny | 2024-03-25 | DC8 | FALSE
Website and User Interface (lead - Ralph, Support - Labib)
| WU1 | Create communication between InfluxDB and Grafana | Ralph | 2023-11-21 | W1 | TRUE
| WU2 | Create graph presets | Ralph | 2023-11-28 | W2 | TRUE
| WU3 | Display Influx cloud data | Ralph | 2024-01-16 | W3 | TRUE
| WU4 | Display data on grafana local from influxdb local | Ralph | 2024-02-27 |  | TRUE
| WU5 | Update Grafana dashboard to suit device requirements | Ralph | 2024-03-25 |  | TRUE
| WU6 | Display costs info | Ralph, Manny | 2024-04-12 |  | TRUE
| WU7 | Stress test Grafana Demo for Design Day | Ralph | 2024-04-12 |  | FALSE
Team Activities and/or Non-Subsystem Related Activities
|  | Create poster for design day |  |  |  | FALSE
FALSE
Key Milestones
| M-1 | Preliminary Design Review | all | 2023-10-05 |  | TRUE
| M-2 | Status Review 1 | all | 2023-10-24 |  | TRUE
| M-3 | Critical Design Review | all | 2024-01-30 |  | TRUE
| M-4 | Alpha Demo | all | 2024-03-05 |  | TRUE
| M-5 | Beta Demo | all | 2024-03-29 |  | TRUE
| M-6 | Design Day | all | 2024-04-19 |  | FALSE

## Action Items
Remember: Action items are not the scheduled projects tasks. All project related technical tasks should be on your “project schedule sheet.” All action items ideally start with a verb describing correctly what needs to be done. Maintain list, keeping OPEN actions and NEW actions at the top. Once the action items are closed and presented, they don't need to be presented again. A unique action ID, responsible person, and a target date are very important.
CreationDate + Action ID | Resp. | Description of the action item (person responsible - target completion date) | Status | Target Completion Date | (If Behind) Support Person | (If Behind) New Completion Date | (If Behind Still) Support Person | (If Behind) New Completion Date
04-09-17-4 | Who | What | Open | 2020-09-12
2023-10-12 | Andrew | NILM toolkit working with our training data we collected | Closed | 2023-10-24
2023-10-12 | Ralph | Setting up grafana environment, configuring presets for grafana | Closed | 2023-10-24
2023-10-12 | Manny | Setup storage method and influxDB, communicating with ESP32 to influx | Closed | 2023-10-24
2023-10-12 | Labib | Find usable open source data, proccessing to have same parameters as ours | Closed | 2023-10-24
2024-01-25 | Ralph | Have static graphs in Grafana showing collected data from InfluxDB | Closed | 2024-01-31
2024-01-25 | Andrew | Train a machine learning model with Pecan Street data | Closed | 2024-02-08
2024-01-25 | Labib | Adding weather history column with API | Closed | 2024-02-08 | Ralph | 2024-02-15 | Andrew | 2024-02-26
2024-02-08 | Ralph | Have specific queries in Grafana graph presets (Predicted/Actual seperated) | Closed | 2024-02-12
2024-02-05 | Manny | Have RPi running docker with home assistant | Closed | 2024-02-23
2024-02-03 | Andrew | Train a final model with all of customer 1 data after weather data is added | Closed | 2024-02-25
2/29/23 | Andrew | Read measurements from influxDB local | Closed | 2024-03-03
2/29/23 | Andrew | Make predictions using ML model and write back to influxDB local | Closed | 2024-03-04
2/29/23 | Ralph | Connect Grafana local to influxDB local to display values | Closed | 2024-03-04
2/29/23 | Labib | Add electricty cost as a metric for each appliance | Closed | 2024-03-04
2024-02-29 | Manny | Have ESP32 sending current measurements to influxDB using ESPHome | Open | 2024-03-04 | Andrew | 2024-03-08
2024-03-07 | Ralph | Test cloud graph presets on RPi | Closed | 2024-03-25
2024-03-07 | Andrew | Run machine learning code on RPi | Closed | 2024-03-25
2024-03-07 | Manny | Use MQTT on ESP32 to send data to home assistant | Closed | 2024-03-25
2024-03-18 | Ralph | Update graphs to include electricity cost | Closed | 2024-03-22
2024-03-21 | Manny & Labib | Set up meeting with Jeremy to discuss network and MQTT options | Open | 2024-03-22
2024-03-21 | Manny | Update budget with CT board and RPi prices | Closed | 2024-03-25
2024-03-21 | Andrew | Check out ethernet cables and micro SD card | Closed | 2024-03-22
2024-04-04 | Manny & Labib | Email Jeremy about router options for creating our own network | Open | 2024-04-05
2024-04-04 | All | Create poster and upload for printing | Closed | 2024-04-12
2024-04-04 | All | Prepare Design Day Slides | Open | 2024-04-18
2024-04-04 | All | Finalize block diagrams | Closed | 2024-04-18
2024-04-04 | All | Write final read me's and documentation | Closed | 2024-04-18
2024-04-04 | Manny | Readme and folder for home assitant and installing add ons | Closed | 2024-04-18
2024-04-04 | Labib | Add text to collab notebooks used as explanation | Closed | 2024-04-18
2024-04-04 | Ralph | Add grafana conenction instructions and json file for dashboard | Open | 2024-04-18
2024-04-04 | Andrew | Add text to collab notebooks and readme for machine learning code | Closed | 2024-04-18
2024-04-04 | Andrew & Labib | Add code to a github repository & share with Huangjie | Open | 2024-04-26
2024-04-18 | Andrew | Email jermery about google form | Open | 2024-04-26
2024-04-18 | Andrew | Add copy of file structure sheet to main readme | Open | 2024-04-26

## Accomplishments
Presented as part of Status review (ECE 484) and Program review (ECE 485)
Summarize any MAJOR accomplishments in the last 2 weeks - Successful functioning, Breakthroughs, Important Checkpoints completed, “Firsts”, Events affecting sponsors\mentors\external parties. List accomplishments and the responsible members for it. Include clear description of various accomplishments. Open a pictures or brief videos if relevant to better explain the accomplishment. Do not include too many technical details. Include funcitonal details.
Subsystem | Brief Accomplishment description | Date of accomplishment | Link to the video or picture describing | Next targetted accomplishment | Notes
Machine Learning - Model (lead - Andrew, Support - Ralph)
| First predicitions made using an ML model | 2023-10-19 | Status Review 1 - Team 50 | Improve accuracy of ML model | Increase length of training & model
| Printed enclosure for ESP32 and CT Board | 2024-01-15 | Enclosure Print1.jpg | N/A | Not related to ML
| ML Predictions written to InfluxDB | 2024-01-20 | InfluxDB Data.jpg | Use Pecan St. data for model verification
| Consildated data and exported a trained model | 2024-02-14 | Program Review 2 | Train model with weather history as another feature | May categorize appliance features
| Categorized data and trained a final model | 2024-02-27 | Program Review 3 | Read and write data from RPi
| Read data from influxDB on RPi | 2024-03-01 | Program Review 3 | Run python code on RPi
| Made predictions and wrote them back to influxDB local | 2024-03-04 | Program Review 3 | Schedule ML code to run real time
| Installed home assistant core using docker | 2024-03-27 | IMG_7929.HEIC | Install add ons for docker instance | Can't install add ons
| Converted tensoflow model to tensorflow lite | 2024-03-29 | CNN LSTM Simplified.ipynb | Package machine learning code as application
| Created application to run machine learning code and cost calculations | 2024-04-01 | application screenshot.JPG | Write documentation for how to use code and improve model
Machine Learning - Preproccessing & Weather API(lead - Labib, Support - Manny)
| Find a open source tool and get a sample data pre-processed and working | 2023-10-22 | Status Review 1 - Team 50 | test out code for a test file and make sure its meeting all the requirements | Figure out how to integrate my subsystem and merge weatherapi.
| Find real time weather data and added weather predictions for next 5 days | 2023-01-25 | CDR -Team 50 | add weather column measuring weather information based on given timestamps | got real time data modify code to show weather history
| added a temparature column (in Farenheit) next to the pre-processed data showing temparature history on the day of testing | 2024-02-27 | Copy of Open Meteo Weather API.ipynb | add power cost analyses columns for each individual appliances in the data table
| added separate columns calculating energy (kwh) and cost for each appliance | 2024-03-04 | Copy of Open Meteo Weather API.ipynb | get the information to Rpi and grafana | not sure if the math is entirely correct, will have to discuss with sponsor/ ge specific rate of electricity for JE household
Data Measurement and Storage (lead - Manny, Support - Andrew)
| Create InfluxDB Bucket and get URL + API Token | 2023-10-22 | Status Review 1 - Team 50 | Finish code to output data | Need to test with current ESP32 Configuration
| Get Homeassistant installed on Raspberry PI (Still need to link with wifi) | 2024-01-21
| Write Homeassist OS to SD Card using RPI imager | 2024-02-15
| Create Home Assistant account and learn the basics of the software | 2024-02-15
| Home assistant OS and add-ons installed | 2024-02-15 | Program Review 2 | Send measurements from CT board to Home Assistant and show values being recorded in InfluxDB
| ESP32 COnnected to homeasssistant | 2024-03-30 |  | Show data being passed to influxdB
Website and User Interface (lead - Ralph, Support - Labib)
| Have an easy access URL for website | 2023-10-19 | Status Review 1 - Team 50 | Connect InfluxDB test environment to Grafana | Need to test before actual environment is prepared.
| Create a few graph presets | 2023-11-16
| Link InfluxDB to Grafana | 2023-11-30 | Critical Review | Show data in Grafana
| Show data in Grafana | 2024-01-30 | CDR Team 50 | Unbounded data
| Query recorded values only in Grafana graphs | 2024-02-19 | Program Review 2 | Have prices for gauges in Grafana graph
| Export graph JSON properly | 2024-03-05 | Alpha Demo | Use consistent titles for easier exporting
| Display data locally and test it | 2024-03-05 | Alpha Demo | Add cost values
| Display cost data | 2024-04-09 | Pre Design Day Review
Team Activities and/or Non-Subsystem Related Activities
| Successful first presentation (PDR) | 2023-10-05 | PDR Team 50 | Status Review 1

## Issues and Help
An issue is an unexpected state or unsettled matter in the present. An issue is not a future concern (that is a risk). Could be technical or project management issue. Do affect project progress. Make sure you describe the issue well. If you do not know the solution then you can say that, there should be an action to find a solution or resolve. Add an extra slide if pictures/diagrams assist you in explaing complex issues.
Issue ID | Responsible person | Date of issue occurence | Issue Description | Potential Solution | Target Date | Help Required? (By Who) | Resolved?
1 | Andrew | 2023-10-30 | Time synchronization with influx and esp32 | Used different connection and NTPClient library | 2023-11-01 | N/A | Y
2 | Andrew | 2023-11-04 | Error calculation yeilds undefined or infite values when measured at each point | Decrease resolution of measurements | 2023-11-27 | Sponsor | Y
3 | Labib | 2023-11-27 | figure out how to unvoid out the date column in file | introduce a new line of code to unvoid the first column | 2024-01-20 | Sponsor | Y
4 | Manny | 2023-11-27 | No longer using a cloud-based solution to send data | Use the raspberry pi to send info to influxdB | 2024-01-20 | N/A | N
5 | Manny | 2023-11-15 | Figure out a way to use Arduino.ide to read the current sensor measurements | Code in Arduino will read the values and send to ESP32 | 2024-01-20 | Sponsor | N
6 | Andrew | 2024-01-19 | Can't load old measured data to influx. Timestamps must be within 30 days | Find and replace dates to be within range | 2024-01-26 | N/A | Y
6 | Andrew & Manny | 2024-01-05 | Cant connect RPi to any network so home assistant OS cant be installed | Share connection from a PC through ethernet | 2024-02-20 | Jeremy | Y
7 | Labib | 2024-02-19 | added a column to the training data for 'temparature', but some of the rows for each hour is returning 'NaN' | reformat the 'timestamp' column so there wouldnt be any formatting issues between the weather api and influx | 2024-02-23 | N/A | Y
8 | Manny | 2024-03-10 | Trouble connecting ESP32 to homeassistanmt running on Rpi. It should connect wirelessly. | Make own temporary wifi network using router. | 2024-03-24 | N/A | N
9 | Andrew | 2024-03-28 | Cannot load files onto raspberry pi easily through web GUI | Use SCP file transfer | 2024-03-30 | N/A | Y
10 | Andrew | 2024-03-29 | Cannot run code efficiently on web GUI for home assistant | Use SSH connection | 2024-03-30 | N/A | Y
11 | Andrew | 2024-03-29 | Cannot run tensorflow or tensorflow lite on home assistant OS | Use home assistant core installation | 2024-04-04 | N/A | Y
12 | Andrew | 2024-03-30 | Home assistant core not compatible with Raspberry Pi | Use docker/container installation of home assistant | 2024-04-02 | N/A | Y
13 | Andrew | 2024-03-30 | Docker home assistant install does not allow for add-ons | Create containers to run integrations such as influx, grafana, and esphome | 2024-04-06 | Forums | Y
14 | Andrew | 2024-04-01 | Neccessary version of influxDB is not compatible and can't be installed as a docker container | Try using newer model of raspberry pi | 2024-04-06 | Forums | Y

## Team performance (hidden)
| Assessment 1 |  | Assessment 2 |  | Assessment 3 |  | Assessment 4
Team performance categories | Scores (out of 5) | Comments | Scores (out of 5) | Comments | Scores (out of 5) | Comments | Scores (out of 5) | Comments
(1) Time is well managed in team
(2) Team is well led by leader
(3) There is equal contribution by all members
(4) Tasks are well-managed within the team
(5) Sponsor/mentor are regularly in communication, updated on project status, meetings run efficiently
(6) Sponsor/mentor is providing adequate help
(7) Product scope is well-managed and under control
(8) Team receives appropriate technical guidance
(9) Team has constructive conflict
(10) Strong Project motivation

## Project Budget
Estimated Tech Demo cost
Part description | Qty | Unit Price | Total Price | Vendor | Link
ESP32 Devkit | 1 | 9.8 | 9.8 | Mouser | https://www.mouser.com/ProductDetail/Espressif-Systems/ESP32-DevKitC-32E?qs=GedFDFLaBXFpgD0kAZWDrQ%3D%3D
Current Transformers (SCT-013) | 8 | 6.9 | 55.2 | Digikey | Digikey
CT Board | 1 | 74.99 | 74.99 | Circuit Setup | https://circuitsetup.us/product/expandable-6-channel-esp32-energy-meter/?v=7516fd43adaa
0
0
0
139.99
Estimated Final Protype cost
Part description | Qty | Unit Price | Total Price | Vendor | Link
Current Transformers (SCT-013) | 2 | 6.9 | 1 |  | https://circuitsetup.us/product/split-single-phase-real-time-whole-house-energy-meter-kit-programmed-esp32-2-cts-abs-box/?v=7516fd43adaa
CT Board | 1 | 74.99 | 0
Raspberry Pi 3 | 1 | 34.99 | 1 |  | https://www.pishop.us/product/raspberry-pi-3-model-b-armv8-with-1g-ram/?src=raspberrypi
2
116.88
Project expense so far
Order number | Link to purchasing sheet | Number of items | Cost
N/A

## Lessons Learned
Add the "Lessons learned" tab in your team charter based on the template here.This is to document what went well and not so well for each team. This tab is to document to yourselves and future projects how you have handled issues you have encountered and resolved.
Lessons Learned
ID | Date Created | Lesson | Impact on Project | Work Around | Experience Gained | Root Cause | Proposed Receiver | Lesson Category (Process, Project Management, Tech/Product) | Comment | Issuer
1 | 2023-10-20 | Implementing old project code or open source toolkits can be difficult | Our current data structure would have to change to use existing toolkits | Create a new ML model to fit our data structures and parameters | Coding machine learning models in python. Working with open source toolkits. | H5 file format and building data structure of nilmtk is not compatible with our data sets | ML Model Lead | Technical |  | Andrew
2 | 2023-10-22 | Accessing a database from another website can be an absolute pain. | Will need a better understanding of server access and permissions. | Sending .csv files instead of using a database but that isn't realistic | Understanding key words that are uniform between websites is crucial. | Lack of database manipulation experience. | Website/UI Lead | Technical |  | Ralph
3 | 2023-11-03 | Mean absolute error percentage calculation doesn't work well if the prediction is 0 or near | Some MAPE calculations for the different features was infinite or undefined | Decrease resolution of the sampling period | Understanding of ways to measure signal/graph statistics | Formula application | ML Model Lead | Technical
4 | 2023-11-27 | using python libraries to make the project more efficient makes the debugging part much harder | the pandas python library might be essential to merge the weather details | using a .csv file from the prev semester's team member to test with | better understanding on python tools | Lack of experience with python | ML Model backup | Technical |  | Labib
5 | 2024-02-15 | Installing Home Assistant on Raspberry Pi is a lot harder than expected | Haults progress on the next steps on data communication betweeen CT board and influxDB | Tried using OdriodN2+ but decided to stick with RPi and used ethernet poert on laptop to share connection | Learned that you can share wifi though ethernet port on laptop to raspberry pi | Lack of expewrience with raspberry pi | Data Communication | Technical |  | Manny
6 | 2024-03-01 | Cannot read local ports through google collab | Cannot run code to connect to local influxDB instance on google collab | Run python script on local machine somewhere | Running python script on local machine | Lack of python experience and google collab enviroment limitations | Data Handling
7 | 2024-03-03 | Library versions not being the same can cause major issues | Machine learning model would not load on local python environment running newer library | Upgrade google collab library version, different file extensions had compatibility | Updgrading libraries on google collab | Not checking the simple cause of problem | ML Model | Technical |  | Andrew
8 | 2024-03-05 | Grafana JSON model needs to have certain titles within the code changed to suit device database | Will require a bit more finesse and work when exporting our graph presets | Create uniform titles for every database we test or use. | Improved comprehension of manipulating graph presets for device. | Coding inexperience. | Website/UI Lead | Technical |  | Ralph
8 | 2024-03-28 | Machine learning models take strong hardware to run if not optimized | ML model cannot run on the Raspberry Pi | Create a windows application to run the model | Trying to run machine learning models on RPi, creating an executable windows application | Hardware limitations | ML Lead | Technical |  | Andrew
8 | 2024-03-28 | Working directly on a raspberry pi is inefficient | A lot of extra time was spent trying to run code directly off the raspberry pi and transfer files | Use SSH to code on the terminal and SCP to transfer files over | Using SHH on Putty and WinSCP for file transfer | Coding inexperience. | Data Handling | Technical |  | Andrew

## Project Risks
Color coding: Yellow: medium impact risk, orange: Medium to high, Red: High and Green: very low impact. Make sure you include correct risk response type: Accept, Transfer, Mitigate or something else. Have the newest and open risks on the top of the list.
Risk ID | Date identified | Description | Risk Category | Risk Response | GO/NO-GO Deadline | Status
1 | 2023-10-19 | Devices with more "random" usage aren't being predicted well with current model | Technical | Improve quality and duration of training data |  | Closed
2 | 2023-10-24 | Using a Csv file format might not be viable for large amounts of data | Technical | Explore different formats if possible |  | Closed
6 | 2024-01-24 | Issues with network installing HomeAssistant operating system on RPi | Technical | Try with different boards and networks |  | Closed
3 | 2024-01-28 | Pecan Street data is extremely large format and is made up of many different houses | Technical | Use one house at a time |  | Closed
4 | 2024-02-02 | Raspbery Pi may run out of storage after measuring data for a long time | Technical | Implement retention period or expand storage |  | Open
5 | 2024-02-05 | Running python along with home asisstant on RPi may be too hardware demanding | Technical | Test on RPi vs. seperate computer |  | Open
6 | 2024-03-05 | Need to be careful with title in Grafana JSON. Wrong bucket/database titles prevents code from working | Technical | Use consistent names in database/code. |  | Closed
7 | 2024-03-29 | Running the machine learning prediction code may not be compatible with the home assistant operating system or our current hardware | Technical | Look for alternative home assistant install method |  | Closed
8 | 2024-04-06 | Weather history API used has a 2 day delay for pulling data. Weather prediction API only gives one temperature per day | Technical | Use another weather API or drop weather as a prediction feature |  | Closed

## Project Timeline_Fold (hidden)
PROJECT STATUS
PROJECT TITLE |  | [Project's title] | [5 empty] | PROTECT NUMBER | [5 empty] | [Project Number] | [17 empty] | * Estimated dates
Team leader |  | [Team Leader's name] | [5 empty] | DATE | [5 empty] | 2020-01-01
| Subsystem Name |  | Task ID | Task detail |  | Resp | Task Dependency | Q1 | [12 empty] | Q2 | [12 empty] | Q3 | [13 empty] | Q4
| Month --> |  |  |  | 2021 |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  |  | SEP |  |  |  |  | OCT |  |  |  |  | NOV |  |  |  |  | DEC
| PROJECT WEEK --> |  |  | Enter the date of the first Monday of each month --> |  | Owner |  | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27
|  |  |  | ECE Semesters | [5 empty] | SPRING 2021 | [16 empty] | SUMMER Break | [12 empty] | FALL 2021
| Class Milestones |  |  | Project agreement | [57 empty] | PROJECT END
Project Requirements Document
Preliminary Design Review | bar: MAR 8
Status review | bar: APR 19
Pitch presentation | bar: APR 19
Critical review | bar: APR 19
Design Day | bar: APR 19
Concept Design Review*
PCB Review*
Alpha Demo*
Beta Demo*
Design Day*
Final Documents*
2 | Power system (lead: Jacob,backup: Sonia) |  | PS1 | Design battery charging circuit |  | Jacob | [34 empty] | 50%
|  |  | PS2 | Simulate charging circuit |  | Jacob | PS1 | [35 empty] | 10%
|  |  | PS3 | Breadboard charging circuit |  | Sonia | PS2 | [40 empty] | 100%
|  |  | PS4 | Design PCB |  | Sonia | PS3 | [43 empty] | 70%
|  |  | PS5 | Submit PCB |  | Jacob | PS4 | [44 empty] | 0%
|  |  | PS6 | Populate PCB |  | Both | PS5
3 | Sensor Controller (lead-Kiera backup-Mithun) |  | SC1 | Explore options of all the sensors and MCUs |  | Mithun | [37 empty] | 100%
|  |  | SC2 | Obtain the parts |  | Kiera | [40 empty] | 50%
|  |  | SC3 | Create the schematic for the sensor interface and test for basic operation |  | Kiera | [40 empty] | 75%
4 | Integration related tasks |  | I1 | Integrate power PCB with controller PCB |  | Kiera and Jacob | [44 empty] | 0%
|  |  | I2 | Determine System Level Testcases |  | All | [41 empty] | 40%

## Project Timeline_S (hidden)
PROJECT STATUS
PROJECT TITLE |  | [Project's title] | [5 empty] | PROTECT NUMBER | [6 empty] | [Project Number] | [14 empty] | * Estimated dates
Team leader |  | [Team Leader's name] | [5 empty] | DATE | [6 empty] | 2020-01-01
| Subsystem Name |  | Task ID | Task detail |  | Resp | Task Dependency | Q1 | [10 empty] | Q2 | [7 empty] | Q3 | [8 empty] | Q4
| Month --> |  |  |  | 2021 |  |  | JAN |  |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  | AUG |  |  | SEP |  |  |  | OCT |  |  |  |  | NOV |  |  |  | DEC
| PROJECT WEEK --> |  |  | Enter the date of the first Monday of each month --> |  | Owner |  | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | SUMMER BREAK |  | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | WINTER BREAK
|  |  |  | ECE Semester |  |  |  | JAN 3: SPRING 2022 |  | FALL 2022
| Class Milestones |  |  | Project agreement | [41 empty] | PROJECT END | bar: JAN 17
Project Requirements Document & Market Slides | bar: FEB 7
System Architecture Diagrams | bar: FEB 14
Preliminary Design Review | bar: FEB 28
Status review | bar: MAR 21
Critical Review | bar: APR 11
Pitch Presentation & Poster | bar: APR 18
CDR
Program Review 1
Program Review 2
Alpha Demo
Program Review 3
Beta Demo
Design Day
Final Docs and Return of Items
2 | Power system (lead: Jacob,backup: Sonia) |  | PS1 | Design battery charging circuit |  | Jacob | [34 empty] | 50%
|  |  | PS2 | Simulate charging circuit |  | Jacob | PS1 | [35 empty] | 10%
|  |  | PS3 | Breadboard charging circuit |  | Sonia | PS2
|  |  | PS4 | Design PCB |  | Sonia | PS3
|  |  | PS5 | Submit PCB |  | Jacob | PS4
|  |  | PS6 | Populate PCB |  | Both | PS5
3 | Sensor Controller (lead-Kiera backup-Mithun) |  | SC1 | Explore options of all the sensors and MCUs |  | Mithun | [37 empty] | 100%
|  |  | SC2 | Obtain the parts |  | Kiera
|  |  | SC3 | Create the schematic for the sensor interface and test for basic operation |  | Kiera
4 | Integration related tasks |  | I1 | Integrate power PCB with controller PCB |  | Kiera and Jacob
|  |  | I2 | Determine System Level Testcases |  | All

## BoM
Part description | Part number | Footprint | Qty | Unit Price | Total Price | Vendor | Link
Power system
1
2
3
4
Sensing System
5
6
7
8
Packaging / Enclosure

## Project abstract
Activity 1) Our project is creating a cost-effective, IoT-driven system to be employed by consumers which will disaggregate various residential loads for analysis.
Activity 2)
Activity 3)
Show Device
Transmitting to InfluxDB
Preprocessing data in InfluxDB
Sending preprocessed data to ML model
Sending disaggregated data back to InfluxDB
Displaying predicted data on Grafana
Activity 4)
|  | Andrew (ML) | Machine learning model disaggregating data, compare to actual
|  | Ralph (Website) | A) Display data B) Receiving data C) Demo by showing live demonstration of website.
|  | Manny (Data Communication) | Show data being read and output/stored in cloud database
|  | Labib (ML) | A and B) finding an open source data set C)showing how a potential one could work

## Manufact&EoL
Follow the format from the tab "Lessons learned" in the team charter template to document the following: -How do you plan on making (process) your device prototype? -How to you see your device being made in high volume? -What will happen at teh devive end of life? -What steps have you taken to minimize the negative effects on the planet for end of life?

## Final Proj Cost
Not for ECE484, Needs to be updated at the end of ECE 485. What you see below is an example.
Part |  | Quantity | Manufacturer Part Number | Vendor Part Number | Price (for 1) | Total | Link to the specific item to be purchased
Order 1
eSUN PLA |  | 1 |  |  | 13.25 | 13.25
Order 2
Ninja Flex 3mm 3D filament (sapphire) |  | 1 | 3DNF0229005 | NIN0229005 | 24.95 | 24.95 | https://www.bhphotovideo.com/c/product/1407515-REG/ninjatek_3dnf0229005_ninjaflex_tpu_flexible_filament.html
Order 3
Capacitor |  | 10 | C1005X5R1A475M050BC | 445-8023-1-ND | 0.38 | 3.8 | https://www.digikey.com/product-detail/en/tdk-corporation/C1005X5R1A475M050BC/445-8023-1-ND/2792141
Capacitor |  | 10 | CL05A105MO5NNNC | 1276-1447-1-ND | 0.049 | 0.49 | https://www.digikey.com/product-detail/en/samsung-electro-mechanics/CL05A105MO5NNNC/1276-1447-1-ND/3889533
Capacitor |  | 10 | GRM188R60J106ME47D | 490-3896-1-ND | 0.259 | 2.59 | https://www.digikey.com/product-detail/en/murata-electronics/GRM188R60J106ME47D/490-3896-1-ND/965938
Capacitor |  | 10 | GRM155R71C104KA88D | 490-3261-1-ND | 0.034 | 0.34 | https://www.digikey.com/product-detail/en/murata-electronics/GRM155R71C104KA88D/490-3261-1-ND/702802
Schottky Diode |  | 5 | BAT20JFILM | 497-3381-1-ND | 0.38 | 1.9 | https://www.digikey.com/product-detail/en/stmicroelectronics/BAT20JFILM/497-3381-1-ND/669138
Yellow LED |  | 10 | LTST-C193KSKT-5A | 160-1831-1-ND | 0.283 | 2.83 | https://www.digikey.com/product-detail/en/lite-on-inc/LTST-C193KSKT-5A/160-1831-1-ND/2356253
Blue LED |  | 10 | LTST-C193TBKT-5A | 160-1827-1-ND | 0.32 | 3.2 | https://www.digikey.com/product-detail/en/lite-on-inc/LTST-C193TBKT-5A/160-1827-1-ND/2355044
Red LED |  | 10 | LTST-C193KRKT-5A | 160-1830-1-ND | 0.283 | 2.83 | https://www.digikey.com/product-detail/en/lite-on-inc/LTST-C193KRKT-5A/160-1830-1-ND/2356251
Micro USB B Connector |  | 5 | 629105136821 | 732-3155-1-ND | 1.21 | 6.05 | https://www.digikey.com/product-detail/en/wurth-electronics-inc/629105136821/732-3155-1-ND/2627308
Connection Header |  | 5 | S2B-PH-K-S(LF)(SN) | 455-1719-ND | 0.17 | 0.85 | https://www.digikey.com/products/en?keywords=S2B-PH-K-S(LF)(SN)
Mosfet |  | 5 | CPH3355-TL-W | CPH3355-TL-WOSCT-ND | 0.41 | 2.05 | https://www.digikey.com/product-detail/en/on-semiconductor/CPH3355-TL-W/CPH3355-TL-WOSCT-ND/8538381
Transistors |  | 5 | MBT3904DW1T1G | MBT3904DW1T1GOSCT-ND | 0.21 | 1.05 | https://www.digikey.com/product-detail/en/on-semiconductor/MBT3904DW1T1G/MBT3904DW1T1GOSCT-ND/918012
10K Resistor |  | 25 | ERJ-2RKF1002X | P10.0KLCT-ND | 0.045 | 1.125 | https://www.digikey.com/product-detail/en/panasonic-electronic-components/ERJ-2RKF1002X/P10.0KLCT-ND/194119
1K Resistor |  | 10 | RC0402FR-071KL | 311-1.00KLRCT-ND | 0.016 | 0.16 | https://www.digikey.com/product-detail/en/yageo/RC0402FR-071KL/311-1.00KLRCT-ND/729460
2K Resistor |  | 10 | ERJ-2RKF2001X | P2.00KLCT-ND | 0.045 | 0.45 | https://www.digikey.com/product-detail/en/panasonic-electronic-components/ERJ-2RKF2001X/P2.00KLCT-ND/194233
100K Resistor |  | 10 | RC0402FR-07100KL | 311-100KLRCT-ND | 0.016 | 0.16 | https://www.digikey.com/product-detail/en/yageo/RC0402FR-07100KL/311-100KLRCT-ND/729473
220 Resistor |  | 15 | ERJ2RKF2200X | P220LCT-ND | 0.053 | 0.795 | https://www.digikey.com/product-detail/en/panasonic-electronic-components/ERJ-2RKF2200X/P220LCT-ND/1746651
27K Resistor |  | 10 | ERJ2RKF2702X | P27.0KLCT-ND | 0.045 | 0.45 | https://www.digikey.com/product-detail/en/panasonic-electronic-components/ERJ-2RKF2702X/P27.0KLCT-ND/1746663
100K Resistor |  | 10 | ERJ-2RKF1003X | P100KLCT-ND | 0.045 | 0.45 | https://www.digikey.com/product-detail/en/panasonic-electronic-components/ERJ-2RKF1003X/P100KLCT-ND/194127
0 Resistor |  | 5 | CRCW04020000Z0EDHP | 541-0.0YBCT-ND | 0.14 | 0.7 | https://www.digikey.com/product-detail/en/vishay-dale/CRCW04020000Z0EDHP/541-0.0YBCT-ND/2223008
Tactile Switch |  | 10 | TL3342F160QG/TR | EG2531CT-ND | 0.679 | 6.79 | https://www.digikey.com/product-detail/en/e-switch/TL3342F160QG-TR/EG2531CT-ND/379004
Slide Switch |  | 5 | PCM12SMTR | 401-2016-1-ND | 0.91 | 4.55 | https://www.digikey.com/product-detail/en/c-k/PCM12SMTR/401-2016-1-ND/1640125
Test Point |  | 30 | 5015 | 36-5015CT-ND | 0.382 | 11.46 | https://www.digikey.com/product-detail/en/keystone-electronics/5015/36-5015CT-ND/278886
Microcontroller |  | 5 | ESP32-WROOM-32D | 1904-1023-1-ND | 3.8 | 19 | https://www.digikey.com/product-detail/en/espressif-systems/ESP32-WROOM-32D/1904-1023-1-ND/9381732
Charger |  | 5 | MCP73831T-2ACI/OT | MCP73831T-2ACI/OTCT-ND | 0.58 | 2.9 | https://www.digikey.com/product-detail/en/microchip-technology/MCP73831T-2ACI-OT/MCP73831T-2ACI-OTCT-ND/1979802
Usb bridge |  | 10 | CP2102N-A01-GQFN24R | 336-4737-1-ND | 1.35 | 13.5 | https://www.digikey.com/product-detail/en/silicon-labs/CP2102N-A01-GQFN24R/336-4737-1-ND/8610993
Voltage Regulator |  | 5 | AP2112K-3.3TRG1 | AP2112K-3.3TRG1DICT-ND | 0.48 | 2.4 | https://www.digikey.com/product-detail/en/diodes-incorporated/AP2112K-3.3TRG1/AP2112K-3.3TRG1DICT-ND/4505257
Accelerometer |  | 10 | LSM6DSMTR | 497-16696-1-ND | 2.697 | 26.97 | https://www.digikey.com/product-detail/en/stmicroelectronics/LSM6DSMTR/497-16696-1-ND/6192778
Order 4
User Tactile Switch |  | 10 | FSM6JSMA | 450-1133-ND | 0.285 | 2.85 | https://www.digikey.com/product-detail/en/te-connectivity-alcoswitch-switches/FSM6JSMA/450-1133-ND/525822
Reset Tactile switch |  | 10 | EVP-BB2A9B000 | P19888CT-ND | 0.563 | 5.63 | https://www.digikey.com/product-detail/en/panasonic-electronic-components/EVP-BB2A9B000/P19888CT-ND/6212411?utm_adgroup=Switches&slid=&gclid=EAIaIQobChMIlvzz2Pyj5QIVFvbjBx0WCAhDEAAYAiAAEgIbEvD_BwE
PCB |  | 10 |  |  |  | 90 | https://makerfabs.com/index.php?route=product/product&path=93_106&product_id=138
Order 5 | [7 empty] | Order 3
500 mAh Battery |  | 2 | 1578 | 1528-1841-ND | 7.95 | 15.9 | https://www.digikey.com/product-detail/en/adafruit-industries-llc/1578/1528-1841-ND/5054539
| Parts: | 304 |  |  | Parts Cost: | 272.42
[5 empty] | Shipping Costs For All orders | 90
[5 empty] | Total Cost | 362.42